# 04 - Technical risk register

Status: DRAFT_FOR_OWNER_REVIEW. Technical source: commit 5eee4b8 (5eee4b8c82a9403b6bb82d5f8d324526f5d6399b, pinned by

docs/bid/bid_technical_baseline_v2.json); every cited path is a file at that commit. Likelihood / impact ratings are

left to the owner (OWNER_INPUT_REQUIRED): the repository holds no risk scoring, and this package does not invent one.

Every mitigation listed already exists in the repository as a plan, framework, rule or owner decision; none is a

demonstrated result.

| id | risk | current state at 5eee4b8 (verbatim statuses) | mitigation that exists in the repository | evidence | rating |
| --- | --- | --- | --- | --- | --- |
| R-01 | Hall transport not validated. No transport closure predicts the Vyovrinda thruster, so no thrust, Isp, efficiency or life can be stated before hardware data. | Gate 3 FAIL; credible set EMPTY; P5-N2 v1 all 9 candidates INCONCLUSIVE / NOT ELIGIBLE (permanent); all absolute 0-D Hall results withdrawn | hardware-first programme; mandatory measured H-1 thrust / feed map drives AG-12 / AG-13; part of the new data pre-registered as held-out Hall-transport validation evidence (workstream W5); promotion only by new predictive evidence, never by retuning | CLAUDE.md "Gate status"; hallthruster_bridge/ensemble/transport_ensemble_v0.json #/members; hallthruster_bridge/validation/VALIDATION_RELEASE_v1.json; docs/decisions/OD_HARDWARE_PIVOT_2026_09_27.json #/workstreams | OWNER_INPUT_REQUIRED (OIR-RSK-01) |
| R-02 | Chemistry validity domain. N2 / N reaction set is complete only for its pre-registered domain (T_e 2-30 eV); in P5-N2 v1, 66 % of run-readings were OUT_OF_DOMAIN (T_e > 30 eV). O / O2 chemistry is DRAFT. | abep-n2n-0.11 COMPLETE_FOR_P5_N2_VALIDATION (domain-limited); v2 Question A disposition A-NO (domain stays at 45 eV mean energy); O / O2 v0 DRAFT_FOR_OWNER_REVIEW, unused; the network-dependent O-table builder docs/chemistry/o_o2/v0/build_tables_nist107_o.py is NOT_RERUN_NETWORK_UNAVAILABLE / UNAFFECTED_BY_FREEZE_CHANGES | no silent extrapolation (rate_validity.toml, chemistry_trustworthy rule); OOD attribution; bounded D-X5 evidence acquisition (published / legitimate access only); v2 pre-registration only on new evidence; NO_ATOMIC_O labelling of O2-bearing ground tests | CLAUDE.md "Gate status" (gate 3); hallthruster_bridge/PINNED.toml; hallthruster_bridge/propellants/rate_validity.toml; docs/forensics/p5_n2_v1/ood_attribution/ood_attribution.json; docs/v2/question_a/QUESTION_A_DISPOSITION.json; docs/chemistry/n2_domain_extension/dx5/dx5_evidence_v1.json; docs/chemistry/o_o2/v0/channel_status_v0.json; docs/decisions/OD_2026_10_04_A9_25_pre_bid_owner_decisions.json #/owner_decision_summary/network_builder | OWNER_INPUT_REQUIRED (OIR-RSK-01) |
| R-03 | Intake drag / delivered-flow gap; upstream closure. The upstream chain may not deliver the flow the thruster needs at every orbit state. | robust upstream set EMPTY_ROBUST_SET_NOT_EVALUATED (0 members) under the frozen 196-state design-state set atmosphere_msis21_orbit_v1_design_states_v2 (F9-DF-01 EMPTY_ROBUST_SET_NOT_EVALUATED); F7 nominal all-state delivered-flow frontier 0.01296 mg/s; 0 Pareto members reach 0.38 mg/s at every state (model-derived, PARAMETRIC_SENSITIVITY); a design finding, not a requirement failure | statewise feed requirement from the measured thrust / feed map (AG-12) instead of a fixed flow gate; owner flow-gap order 1 PERFORMANCE_DERIVED_H1_FEED_REQUIREMENT; 2 CAPTURE_COLLECTION; 3 COMPRESSOR_DOMAIN_PUMPING_FEED_EFFICIENCY; 4 SCHEDULED_SETPOINT; closing tests on the turbo-row coefficients (compressor down-select T-1 / T-2); no requirement relaxation (A9.13 S6.13 / OQ-F4-04) | docs/architecture/freeze_candidate/architecture_freeze_candidate_v1.json #/design_findings_for_owner[id=F9-DF-01], #/upstream_pareto/robust_set; docs/design_synthesis/f7_f8_optimizer/f7_f8_optimizer_v1.json #/findings[id=F78-02], [id=F8-01]; docs/architecture_comparison/compressor_downselect/compressor_downselect_v2.json; abep_sim/data/atmosphere_msis21_orbit_v1_design_states_v2.json | OWNER_INPUT_REQUIRED (OIR-RSK-01) |
| R-04 | Life / erosion. > 15,000 h firing and 26,280 h mission not supported by any admissible analysis. | RVM-12 / RVM-13 NOT_EVALUATED; wall-life needs an admitted closure (none) | pre-registered wear / endurance segments (AOL-LF-02); life analysis that uses no withdrawn number (AOL-LF-01); magnetically shielded topology T2 chosen for H-1 (H1F-MC-01; no life benefit is claimed) | docs/experiments/lifetime_ao/ao_lifetime_register_v5.json; docs/requirements/rvm_a9/rvm_a9_v1.json #/rows[id=RVM-12]; docs/hardware/h1_freeze_candidate/h1_freeze_candidate_v1.json | OWNER_INPUT_REQUIRED (OIR-RSK-01) |
| R-05 | Atomic oxygen (intake, compressor, thruster, anode, ICP plasma-facing surfaces, collector / bias electrode, gas path). | RVM-16 INCOMPLETE_EVIDENCE: 44 application x candidate screens all INCOMPLETE_EVIDENCE; no AO / oxidation / sputter evidence on any candidate; current-architecture reading OWNER_CONFIRMED_CURRENT_ARCHITECTURE_READING (no flight keeper; graphite not the current flight baseline for O / AO-exposed plasma-facing or electron-source surfaces until coupon evidence) | AO register v5 (witness coupons, ground AO exposure with fluence witness, post-test SEM / EDS / XPS); P4 fail-closed screens; academic AO collaboration (RFP-P27-02) | docs/experiments/lifetime_ao/ao_lifetime_register_v5.json; docs/experiments/hall_icp/p4_anode_materials/p4_anode_materials_v1.json; docs/requirements/rvm_a9/rvm_a9_v1.json #/rows[id=RVM-16] | OWNER_INPUT_REQUIRED (OIR-RSK-01) |
| R-06 | Thermal closure. Coupled H-1 / ICP and anode thermal closure not achieved; the >= 50 K margin requirement (RVM-17) is recorded against an H2-5 analog margin of 11.2 K (recorder flag). | ICP_COUPLED_THERMAL UNRESOLVED; ANODE_THERMAL_CLOSURE UNRESOLVED; 0 heat terms evaluated on evidenced inputs; the inherited P3 cathode node is NOT_USABLE_FOR_FLIGHT_THERMAL_CLOSURE (AFI-03); never reported as a thermal pass | P3 coupled-thermal framework (Q_Hall->ICP, Q_collector, Q_RF/match, Q_plume, view factors) fed by P1 / P2 / coupled-run data; successor cathodeless thermal model (post-bid); thermal-vacuum test with measured sink temperature; anode heat-removal redesign (A9.2 investigation list) | docs/experiments/hall_icp/p3_coupled_thermal/p3_coupled_thermal_v2.json; docs/requirements/rvm_a9/rvm_a9_v1.json #/rows[id=RVM-17]; docs/decisions/OD_2026_10_04_A9_25_pre_bid_owner_decisions.json #/owner_decision_summary/AFI-03; CLAUDE.md section "A9" (recorder flags) | OWNER_INPUT_REQUIRED (OIR-RSK-01) |
| R-07 | Mass closure (< 40 kg wet) not yet achieved. The current provisional planning / evidence roll-up does not yet close the requirement. | MASS INCOMPLETE_EVIDENCE / NOT_YET_CLOSED; current provisional planning / evidence roll-up (mass_power_a9_v5): dry 38.35 kg after a 10 % system margin; wet 40.35 / 43.35 / 48.35 kg at the 2 / 5 / 10 kg Xe planning / sensitivity cases (DOES_NOT_CLOSE in all 3 cases vs < 40 kg); no CBE, no measured mass; AG-11 INCOMPLETE_EVIDENCE (no CBE; AL-04 / AL-07 / AL-08 below evidence floors); flight Xe load NOT FROZEN | proposal design target nominal dry <= 34.0 kg with a 10 % system margin and the 2 kg Xe planning reference -> 39.4 kg wet (DESIGN TARGET, not evidence); mass-closure actions: AL-07 current cathodeless PPU CBE / requote; AL-08 quote / design rebase; AL-04 completed Hall-head CBE; AL-09 design-derived CBE; actual routed harness; subsystem integration / structural optimization; requirement not relaxed and no line reduced to force closure (MQ-10; A9.26); DISC-02 wet / dry clarification with DRDO | docs/budgets/mass_power_a9_v5/mass_power_a9_v5.json #/rollups[configuration=hall_icp_neutralizer]; docs/architecture/freeze_candidate/architecture_freeze_candidate_v1.json #/architecture_gates[id=AG-11]; docs/decisions/OD_2026_10_04_A9_25_pre_bid_owner_decisions.json #/owner_decision_summary/bid_mass_wording; docs/decisions/OD_2026_10_05_A9_26_mass_budget_owner_decisions.json | OWNER_INPUT_REQUIRED (OIR-RSK-01) |
| R-08 | Anode material. | 316L REJECTED_AS_CURRENT_BASELINE; final anode material OPEN; operating temperature TBD | P4 candidate-material trade at reduced operating temperature; LOCK-2 thresholds frozen before acceptance-bearing exposure; replaceable serialized anode (H1F-AN-11) | docs/experiments/hall_icp/p4_anode_materials/p4_anode_materials_v1.json; docs/hardware/h1_freeze_candidate/h1_freeze_candidate_v1.json | OWNER_INPUT_REQUIRED (OIR-RSK-01) |
| R-09 | Single RF-ICP electron source, no hollow-cathode fallback in flight (A9.19; C1 GROUND_REFERENCE_ONLY). Insufficient electron current, RF power per ampere or ignition would leave no flight alternative. | ICP electron-current capacity PENDING_ICP45; ICP45 NOT_EVALUATED; RF power closure PENDING_HARDWARE; RF ratings TBD_AFTER_IMPEDANCE_MAP; GNG-ICP-01 NOT_EVALUATED | mandatory fail-closed GNG-ICP-01 before LOCK-1; C1 ground reference as bench control only (C1-vs-ICP on matched modules); ICP-45A -> ICP-45N -> ICP-XE-MODE campaigns; P2 impedance map | docs/architecture/freeze_candidate/architecture_freeze_candidate_v1.json #/pre_lock1_gates[id=GNG-ICP-01], #/a9_2_statuses; docs/experiments/hall_icp/programme/hw_programme_a9_21_v1.json #/steps | OWNER_INPUT_REQUIRED (OIR-RSK-01) |
| R-10 | Bus power < 1.5 kW not closed. | ledger PARTIAL_BOUNDARY; 22 loads TBD; P_bus,1ms,max NOT_EVALUABLE in all 7 steps; AG-10 PARTIAL_BOUNDARY | frozen gate definition and metering spec; 1350 W internal allocation with P_ICP,available rule; ledger efficiencies pre-registered at LOCK-1 | docs/architecture_comparison/power_boundary_a9_v2/bus_power_boundary_a9_v2.json #/gates_and_allocations; docs/requirements/rvm_a9/rvm_a9_v1.json #/rows[id=RVM-04] | OWNER_INPUT_REQUIRED (OIR-RSK-01) |
| R-11 | Mission inputs not supplied by the RFP (inclination / LTAN, AOCS pointing envelope, host-spacecraft drag ICD). Without them AG-13 cannot be evaluated. | A9.21 EXTERNAL_INPUTS: stay TBD; no code default used as mission truth; design-state set BROAD_ENVELOPE_ALL_INCLINATIONS_ALL_LTAN_NOT_MISSION_ICD; spacecraft drag basis REFERENCE_PARAMETRIC_NOT_FLIGHT | request from DRDO at PDR; reference / parametric drag basis for interim studies only; a registered orbit narrows the design-state set in a new version | docs/decisions/OD_2026_10_02_A9_21_open_items_and_hardware_programme_owner_decisions.json #/decisions/EXTERNAL_INPUTS; docs/design_synthesis/spacecraft_reference_drag/spacecraft_reference_drag_v1.json | OWNER_INPUT_REQUIRED (OIR-RSK-01) |
| R-12 | Redundancy not designed. Meeting RFP-P18-02 / -09 adds mass and power to a mass budget that is not yet closed. | RVM-19 NOT_EVALUATED (no electronics selected) | FMEA at PDR-1; owner redundancy concept (OIR-TEC-02) | docs/requirements/rvm_a9/rvm_a9_v1.json #/rows[id=RVM-19] | OWNER_INPUT_REQUIRED (OIR-RSK-01) |
| R-13 | Requirement readings not closed with DRDO. RFP pages 1-15 and 34-40 not screened or transcribed by the repository (formats / annexures unchecked); DISC-01..10 open readings. AG-15 (requirement basis) is closed. | AG-15 DETERMINING_EVIDENCE_PRESENT_NO_REMAINING_CONDITION; pages 1-15 / 34-40: owner page review OWNER_REVIEWED_NO_ADDITIONAL_TECHNICAL_PERFORMANCE_REQUIREMENT (A9.22 G3: technical-performance requirements only) | owner page review (OIR-DOC-01); DRDO clarifications for DISC-02 / -03 / -05 / -07 / -09 | docs/requirements/rfp_official/rfp_registration_v1.json #/page_coverage; docs/architecture/freeze_candidate/architecture_freeze_candidate_v1.json #/architecture_gates[id=AG-15] | OWNER_INPUT_REQUIRED (OIR-RSK-01) |

## Upstream basis (owner decision; replaces the earlier post-freeze caveat)

The earlier draft cited five hand-picked orbit-averaged design states and carried a post-freeze caveat recorded in the

historical v1 freeze record (docs/bid/bid_technical_baseline.json). The owner resolved it (A9.24 item 9, "Choose B"):

the package is re-frozen on a later verified technical source that includes the frozen 196-state design-state set

(abep_sim/data/atmosphere_msis21_orbit_v1_design_states_v2.json). At 5eee4b8 the robust upstream set is EMPTY (F9-DF-01 EMPTY_ROBUST_SET_NOT_EVALUATED); this package therefore claims no

robust upstream (intake / compressor / feed) closure anywhere, and cites the upstream results only as recorded at the

technical source.